## Sheet1
PROJECT SCHEDULE TEMPLATE
Logic Circuit Interactive Sim | Manager - David C.
PROJECT DELIVERABLE
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
2025-10-01 | 2025-12-05 | 0%
TASK NAME | ASSIGNED TO | DONE BY | STATUS | COMMENTS
Iteration 3 submission | ALL | 2025-11-05 | Completed | requirements on Canvas
Team meeting | ALL | 2025-11-04 | Completed | will work on next steps of project together (meeting ~2pm in Snell)
Additional Info for Logic Gates | Bethany | 2025-11-09 | In progress
Add logic to sprites | Kyra | 2025-11-09 | In progress | have AND/OR/NAND/etc have 2/3/4 inputs
First draft of GUI, Loading sprites | David | 2025-11-09 | In progress
WK 6 - Basic program funtions, see tasks | ALL | 2025-11-16
research saving methods and handling invalid circuit designs | TBD | 2025-11-11 | Not Started | users can store circuit designs as a JSON or XML file, and Create error messages for invalid circuit designs
Add more advanced gates |  |  |  | suggested: T/D/JK Flip-Flop, S/R Latch, D-Latch
Final Report | ALL | 2025-12-05 | Not Started